## Monitor - PUBLIC
Monitoring Table Of Actions
Action Code | UAEU Partnership | Action Plan | Action | Short summary | Better Regulation [in order of priority] | Better Funding [in order of priority] | Better Knowledge [in order of priority] | Action category | Specification if other action category | Date of the official delivery of the Action Plan | Starting Date of Implementation | Action Implementation Status | Date by which the Partnership intends to finalise implementing this action | Outputs under preparation | Outputs delivered up to now | Outcomes already achieved | Changes in the organisational structure | Please specify | Please specify | Additional information about the implementation of this action
CCH08 | Culture and Cultural Heritage | Action Plan 1 (elaborated in 2021) | Guiding Principles for Resilience and Integrated Approaches in Risk and Heritage Management in European Cities | The overall objective of this Action is to foster the integration of urban built heritage into Disaster Risk Management (DRM), climate change and environmental plans and policies at the local level. To achieve this, the Action aims at establishing recommendations and guiding principles for relevant local authorities and other relevant actors, including citizens. | 2 | 3 | 1 | Guidance documents/Handbooks |  | 2020/10/21 | 2021-01-01 | Advanced implementation | 2026-06-01 | Practice check and verification of handbook (in DE) for the local level (published in late 2023) with approximately three cities | > Guidance Paper on Integrated Risk Management (in EN), see also https://www.bbsr.bund.de/BBSR/EN/research/programs/ExWoSt/FieldsOfResearch/resilience-builtheritage/01-start.html > Policy Recommendations for EU, Member State and local level > articles > presentations > workshops | Increased visibility for the topic at national and local levels, knowledge exchange (Action Group as "network of networks") | Yes, one or more of the participating members changed (please specify) |  | Changing members of the Action Group, e.g. ICOMOS, UNESCO
CCH10 | Culture and Cultural Heritage | Action Plan 1 (elaborated in 2021) | Integrated Approaches to Dissonant Heritage | This Action focuses on how to strengthen the “Dissonant” (or controversial) cultural heritage by integrating it in urban and regional planning as well as tourism concepts as a fundamental mean to educate, transmit history and nurture democracy building in Europe while – at the same time – enabling those stigmatised neglected areas to use their local economic and touristic potential. The Action focuses particularly on the Dissonant Heritage of the 20th century in smaller towns and peripheral regions. | 3 | 2 | 1 | Toolkit |  | 2020/10/21 | 2021-01-01 | Advanced implementation | 2025-06-30 | Toolbox for integrated approaches at the local level is currently being develope, to be published by the summer of 2025 in EN and DE. | > Orientation Paper (2022) > Booklet 10 (Policy Recommendations for the EU, Member State and city levels > presentations > international workshops > two websites: www.dissonant-heritage.eu (research project), www.dissonant-heritage.info (networking) | Increased awareness for the topic both at EU (e.g. in the framework of the Cultural Heritage Label) and national levels; the Dissonant Heritage Action Group as a "network of networks" and an open platform with its own projects. | Yes, one or more of the participating members changed (please specify) |  | The Action Group has a growing number of external participating members.
CCH07 | Culture and Cultural Heritage | Action Plan 1 (elaborated in 2021) | Data Collection and Smart Use Applied to the Management of Tourist Flows | Data collection and analysis are key factors for implementing monitoring systems of tourist flows in order to balance overcrowded destinations and less visited sites. This Action proposes an IT tool that has been delivered and tested, “Feel Florence” a new app suggesting unusual itineraries in the city, in the neighborhoods and in the metropolitan area, to bring people closer to local experiences and to get to better know the city and its typical features. ICT tools for promoting the Smart Destinations tourist offer can increase the ability of cities to orient/manage visitor’s flows. In the end, this will lead to more balanced tourist flows, an increased quality of the cultural experience and a better quality of life for the local population. | 1 | 3 | 1 | Policy Recommendations |  | 2020/10/21 | 2019-02-21 | Sustainability secured | 2022-06-21 | FeelFlorence project is constantly updated and new functionalities have been added. https://www.feelflorence.it/en FeelFlorence is a mobile app and a website connected to a Content Management System and a BigData platform that suggests unusual itineraries in the city, in the neighbourhoods and in the metropolitan area, to bring tourists closer to local experiences. Through real-time detection of the presences in the city and predictive analysis, this tool provides alert notifications on the most congested areas allowing tourists to avoid overcrowded destinations, stay updated on events and initiatives and better organize their stay and their visit schedule. | > Self-evaluation toolkit to support local authorities in designing policy for sustainable tourism realized with JRC > FeelFlorence App is available for free download. > Half day workshop on FeelFlorence for replication in other cities/regions > Recommendations and proposals for an in-depth analysis of tourism flows of an urban reality for a better governance of the destination realized by Centro Studi Turistici di firenze (Targeted Support) > Recommendations to EU: a. Make easier data access and sharing for public interest to enhance Smart Destination planning and management and improve ICT tools in order to tackle the phenomena more efficiently, thus promoting sustainable tourism, livability and well-being. b. Capitalize the experience of the UP-CCH in the current programming period 2021-2027 to boost the role of cities as driver of sustainable and inclusive development, cradle of innovation and adequate scale for demonstration and experimentation. | - In depth reflection on existing indicator sets for measuring the tourism sustainability and their possible integration with qualitative KPIs - Improvement of the Smart Destination planning through FeelFlorence: smart management to balance tourist flows between major tourist hubs and less visited sites and better enjoy the city thanks to push notification system based on real time data | No |  |  | -
CCH11 | Culture and Cultural Heritage | Action Plan 1 (elaborated in 2021) | Local Cultural Services Fostering Social Inclusion: Identification of Cities’ Research Needs and Peer Learning | The Action is aimed at identifying cities’ specific research needs (through cultural leaders from city administration) to better plan future EU calls for proposals on research, to guarantee that the results of these research projects are used at the local level to improve cultural policies, to contribute to the overall reinforcement of cultural offers in European cities. | 2 | 3 | 1 | Other (please specify) | Identification of cities' research needs | 2020/10/21 | 2021-11-01 | Finalised | 2021-11-01 | A table recapping the results of our research on cities' research/learning needs on issues linked to culture and social inclusion has been finalised An online knowledge sharing event has been organised | Please see the response above. The action is finished as all deliverables were finalised during the lifespan of the urban partnership action on culture and cultural heritage | - the output of the action has been widely shared among the partnership and European stakeholders - leading to increased awareness of cities' research needs on culture and social inclusion | No
PP-PLAN2-01 | Public Procurement | Action Plan 2 (elaborated in 2022)" | Reflection board supported by a sustainable platform where cities, regions, member states and the European Commission / institutions exchange ideas and experiences on strategic public procurement | This Action will develop the network, increase its membership and develop its role and influence. It will develop a reflection board supported by a sustainable (online) platform, where cities, regions, member states and the European Commission co-develop public procurement practices and exchange ideas and knowledge within the Urban Agenda Partnership community of procurers. | 2 | 3 | 1 | Other (please specify) | 1. Platform 2. Position Paper 3. Update of the Legal Framework module (deliverable of Action Plan 1) | 2022/03/21 (2nd Action Plan) | 2022-03-21 | Advanced implementation | 2024-12-01 | > Platform website ( Action 1 of the Action Plan 2022) > Dissemination of the Position Paper with key recommendations on public procurement (Action 1 of the Action Plan 2022) > Dissemination of the trainings and briefings on public procurement (Action 2 of the Action Plan 2022) | Action 1: > Draft version platform is ready > Position Paper is finilised > E-Learning module Legal framework is finilised Action 2: > Briefings, trainings and webinars are delivered and recordings are published on EU funded PROCEDIN website Action 3: > Economy Recovery through procurement best practices are collected > Article about Economy Recovery is published | Action 1: > Awareness raising and advocacy about strategic role of public procurement (through Position Paper) > Capacity building of procurers, sustainability advisors, decision makers on strategic public procurement (thanks to updated E-Learning on Legal Framework of Innovative and Responsible Public Procurement Action 2: > Awareniss raising and capacity building of procurers, sustainability advisors, decision makers, SMEs and anyone who is interested in public procurement as a strategic tool (through webinars, workshops, trainings, resource database, tools and materials thanks to synergies of Urban Agenda PP and EU funded PROCEDIN project) Action 3: > Public authorities learned how to recovery (local) economy using procurement as a strategic tool (through 10-ways guide) | No
[5 empty] | 10 | 6 | 15
3 Active partnerships
5 Actions
reported
November
2024
Better Knowledge
Better Funding
Better Regulation