## Content
Monitoring Table Of Actions
Date | 2025-09-01
Classification | PUBLIC
Action Code | UAEU Partnership | Action Plan | Action | Short summary | Has the action aim changed compared to the initial description? | Updated action description | Better Regulation [in order of priority] | Better Funding [in order of priority] | Better Knowledge [in order of priority] | Action category | Specification if other action category | Starting Date of Implementation | Action Implementation Status | Date by which the Partnership intends to finalise implementing this action | Outputs under preparation | Outputs delivered up to now | Outcomes already achieved | Changes in the organisational structure | Please specify | Cross-Cutting Issues addressed by the Action | Contribution to the New Urban Agenda (of the HABITAT III) | Additional information about the implementation of the action
PP-Plan3-01 | Public Procurement | Action Plan 3 (elaborated in 2025) | Capacity building for Public Procurement as a Strategic tool | Public procurement is an important strategic tool that helps cities to deal with different economic, environmental, and social (including gender-responsible) challenges. It is no longer seen as only of interest to public buyers and budget holders, but also as highly relevant to government leaders and stakeholders as they address key policy priorities. The connection between the budget holders and decision makers is essential for responsible public procurement efforts to succeed. Action 1 will contribute to the further capacity building and knowledge development in this network, increase membership and community, and develop its role and influence. The main focus of this action will be on Innovation, Circular Procurement, Socially Responsible Public Procurement and the Professionalisation of Public Procurement. | No | N/A | 2 | 3 | 1 | Guidance documents/Handbooks |  | 19/5/2025 | Half implementation | 31/12/2027 | 1. Webinar on Decarbonisation through Public Procurement; 2. Webinar on E-Learning modules developed by this UA Partnership | Webinar on Circular Procurement | Awareness rising and capacity building on Innovative and Responsible Strategic Public Procurement | No |  | a) Promoting urban policy for the common good, inclusiveness, accessibility, security and equality. | with outcomes, already delivered and those in progress
PP-Plan3-02 | Public Procurement | Action Plan 3 (elaborated in 2025) | Advocacy for better regulation | The EU Directives on Public Procurement might be revised during the 2024-2029 Commission mandate. The Urban Agenda Partnership on Innovative and Responsible Public Procurement for the EU aims to provide the Commission with input and recommendations throughout this process. | No | N/A | 1 | 3 | 2 | Modification to existing EU legislation |  | 19/5/2025 | Half implementation | 31/12/2027 | Recommendations on revision of the EU legislation on Public Procurement | 1. Position Paper with recommendations; 2. Position Paper with practical examples showcasing the meaning of the recommendations; 3. Questionnaire as input for the revision of the EU legislation on Public Procurement | EC is provided with recommendations, based on practical experience and insights of cities, regions, member states | No |  | a) Promoting urban policy for the common good, inclusiveness, accessibility, security and equality.;b) Enhancing integrated and innovative approaches, notably through financing and in correlation to the green, digital and just transitions.; g) Contributing to the acceleration of the implementation of the 2030 Agenda SDGs, the New Urban Agenda and Habitat III principles. | With more strategic use of public procurement
PP-Plan3-03 | Public Procurement | Action Plan 3 (elaborated in 2025) | Better funding to stimulate strategic procurement | As part of this action recommendations on how to use funding to stimulate Public Procurement as a Strategic tool will be provided. Better funding on Strategic Procurement will help European public authorities to overcome challenges they are dealing with, such as climate adaptation, energy transition, circular economy and competitiveness. | No | N/A | 3 | 1 | 2 | Policy Recommendations |  | 19/5/2025 | Initial implementation | 31/12/2027 | In-depth survey and interviews | 1. Survey about funding needs and obstacles; 2. Analysis of the survey results | General insights about funding needs that would help to stimulate public procurement as a strategic tool | No |  | c) Supporting effective urban governance, participation, and co-creation; g) Contributing to the acceleration of the implementation of the 2030 Agenda SDGs, the New Urban Agenda and Habitat III principles. | Not yet, but will contribute to more use of ecosystems, stimulate innovation made in Europe etc
ST-PLAN1-01 | Sustainable Tourism | Action Plan 1 (elaborated in 2024) | Guidelines for enabling climatefriendly and resilient urban destinations | The action aims to generate guidelines focused on how urban destinations can develop climate action plans, communicate them, promote climate-friendly offer, attract climate-friendly demand, and promote better tourists’ behavior within destinations | No | N/A | 3 | 2 | 1 | Guidance documents/Handbooks |  | 2025-01-04 | Advanced implementation | 31/03/2026 | Local dissemination events of the guidelines | 1. Guidelines for enabling climate friendly and resilient urban destinations. The Guidelines are grounded in real-world practices from European destinations. Nine examples (from island regions to heritage cities) illustrate how local administrations are tackling tourism’s climate impact through planning, regulation, capacity-building, and cooperation across governance levels.They provide a step-by-step methodology to help local authorities: • Evaluate their current climate vulnerabilities and tourism impacts • Identify priority areas for action • Engage stakeholders across sectors • Define long-term climate objectives for tourismIntegrate these objectives into local planning frameworks and tourism strategies. Webinar to disseminate the guidelines (December, 2 2025) | Capacity building of tourism and climate officers, urban planners, and local decision-makers to explore how to kick-start or improve their journey toward greener tourism. | No |  | b) Enhancing integrated and innovative approaches, notably through financing and in correlation to the green, digital and just transitions.;c) Supporting effective urban governance, participation, and co-creation.;d) Promoting multi-level governance and cooperation across administrative boundaries.;e) Harmonising measures at different spatial levels and implementing place-based policies and strategies. | The action considers as a reference methodologies, tools and good practices offered by the Covenant of Mayors, as well as the EU Missions on Adaptation and Climate Neutral and Smart Cities, Green Deal initiatives for cities, such as the Green Capital and Green Leaf awards, the Green City Accord, the EU Cities Mission, the Circular Cities and Regions Initiative, the Smart Cities Marketplace, CIVITAS on urban mobility Living.in.EU and others.
ST-PLAN1-04 | Sustainable Tourism | Action Plan 1 (elaborated in 2024) | More resilient and sustainable destinations through diversification of tourism offer | This action contributes to existing efforts to gather knowledge on challenges, opportunities, measurement, and lessons learned, particularly through the collection and analysis of good practices. The action explores available funding opportunities and recommend optimal ways to utilize these funds and propose how funding structures can be amended to better support diversification. The recommendations regarding financial incentives for diversifying the tourism offer can also provide opportunities for improving relevant regulations at many governance levels. | No | N/A | 1 | 1 | 1 | Guidance documents/Handbooks |  | 2025-01-04 | Advanced implementation | 2026-01-06 | 1. Partners are actively uploading materials for the Handbook drafting. 2. Several meetings with external experts have been conducted so far in order to design clear and concise content for the creation of the Handbook. 3. A list of relevant key stakeholders has been finalized, and the surveys are ready to be launched. 4. A handbook for creating a suitable environment and assumptions for accessible tourism and tourism for all in urban destinations (based on survey results, previous research, best practices and other relevant literature) is currently under preparation. 5. Two dedicated workshops will be organized once the handbook is completed to promote the handbook, test draft recommendations, share lessons learned and present good practices. | A concise action survey has been finalized and will be distributed to all partners. The results will undoubtedly be of great value and will be included in the Handbook for urban authorities and stakeholders. | Collection of information on practices in urban destinations has been finalized. To ensure that the recommendations reach the intended target, partners will organise dedicated dissemination activities (conferences or workshops), inviting identified good practices to present their experinces. Local residents will be informed better and more engaged with sustainable tourism efforts. | No |  | a) Promoting urban policy for the common good, inclusiveness, accessibility, security and equality. | By implementation of this action the contribution to the New Urban Agenda is seen by the fact that cities mitigate risks associated with touirism chocks, such as pandemics, geopolitical crises and climate change. It also encourages decentralized tourism flows, reducing the vulnerability of specific zones and enhancing adaptive capacity. Diversifying the tourism offer reduces dependency on a single type of tourism or season, making destinations more resilient to crises like pandemics, natural disasters, or market changes. Diversifying tourism disperses visitors beyond city centers to rural and peri-urban areas, enhancing balanced development and reducing urban congestion. Cities can integrate tourism diversification into their Urban Development Plans, use urban planning tools to identify underutilized areas with tourism potential or involve local communities in planning and managing diversified tourism.
ST-PLAN1-05 | Sustainable Tourism | Action Plan 1 (elaborated in 2024) | Destinations accessible for all | The action explores opportunities to contribute to the Better Knowledge pillar, aiming to gather information on accessibility challenges and practices in urban destinations. However, considering recent relevant legislative developments, the outcomes of this action can also contribute to better implementation of EUlevel accessibility-related legislation. | No | N/A | 1 | 2 | 1 | Guidance documents/Handbooks |  | 31/1/2025 | Advanced implementation | 2026-01-06 | 1. Partners are actively uploading material s for Handbook drafting. 2. Several preparatory meetings with external experts have been organized. 3. Dissemination activities are being planned. 4. A list of relevant and key stakeholders has been finalized, and the surveys are ready to be launched. 5. A handbook for creating a suitable environment and assumptions for accessible tourism and tourism for all in urban destinations is currently under preparation. It will be developed based on insights from surveys, previous studies, recognized best practices, and relevant academic literature. | A detailed survey of relevant stakeholders has been finalized. It is designed to gather data on existing accessibility practices across urban destionations in the EU. The results of the survey will greatly assist in the creation of the handbook. | A dedicated survey to collect information relevant to existing practices on accessibility in tourism urban destinations is ongoing. This survey will be disseminated within and outside the partnership in order to reach a wide range of practices across the EU. Identifying good practices, reflecting on lessons learned and drafting recommendations for urban authorities and for better implementation of EU level accessibility regulations is in the focus of this action. This activity will consist in pooling all the knowledge collected into a handbook that would cover recommendations, based on best practices and lessons learned. To ensure that the recommendations reach the intended target, partners will organise dedicated dissemination activities, inviting identified good practices to present their experiences. Most segnificant impacts of this action are enchanced knowledge at local and regional levels, and raised awareness among local communities. | No |  | a) Promoting urban policy for the common good, inclusiveness, accessibility, security and equality. | Making "Destinations Accessible for All" is not just a tourism goal, it is a human right and urban development imperative aligned with the New Urban Agenda's vision for inclusive, safe, and equitable cities for all people.
GC-Plan1-01 | Greening Cities | Action Plan 1 (elaborated in 2024) | Need for green - Methodology for quantifying the demand for green infrastructure at local leve | This Action will provide a methodology to serve as a tool for municipalities in defining their demand/need for urban green infrastructure, which would serve a dual purpose: (1) fulfilling climate adaptation needs, while enhancing biodiversity needs (2) ensuring an evidencebased substantiation for green infrastructure | No | N/A | 2 | 2 | 1 | Toolkit |  | 2025-01-02 | Advanced implementation | 2026-06-03 | Final online portal. All outputs have been delivered. Final minor observations are pending for deliverable consolidation. | Draft online portal. All outputs have been delivered. Final minor observations are pending for deliverable consolidation. | N/A | No |  | a) Promoting urban policy for the common good, inclusiveness, accessibility, security and equality. b) Enhancing integrated and innovative approaches, notably through financing and in correlation to the green, digital and just transitions; f) Supporting sound and strategic sustainable urban planning, and balanced territorial development; g) Contributing to the acceleration of the implementation of the 2030 Agenda SDGs, the New Urban Agenda and Habitat III principles. | Action 1 contributes to the NUA chiefly by delivering a municipal-grade implementation toolchain (baseline data + shared definitions + participatory validation + spatial analysis + forecasting + monitoring) that makes the NUA’s commitments on green public spaces, resilience, ecosystem-based approaches, integrated planning, and evidence-based governance practically executable.
GC-Plan1-02 | Greening Cities | Action Plan 1 (elaborated in 2024) | Indicator system for Urban Nature Plans | This Action will develop a proposal for an indicator system local authorities, representing towns and cities with more than 20,000 inhabitants, can use to measure and monitor progress against their Urban Nature Plans, in line with the targets of the EU Biodiversity Strategy for 2030 and the Nature Restoration Regulation for urban areas and ecosystems. It will include a small set of core and supplementary indicators, clustered under different thematic areas of assessment. | No | N/A | 2 | 1 | 1 | Data and indicators |  | 15/11/2024 | Finalised | 28/02/2026 | The Action deliverable has been finalized and has been sent to the EUI for layout development | Monitoring and evaluation guidance | Monitoring and evaluation guidance | No |  | a) Promoting urban policy for the common good, inclusiveness, accessibility, security and equality.; b) Enhancing integrated and innovative approaches, notably through financing and in correlation to the green, digital and just transitions; c) Supporting effective urban governance, participation, and co-creation; d) Promoting multi-level governance and cooperation across administrative boundaries; e) Harmonising measures at different spatial levels and implementing place-based policies and strategies; f) Supporting sound and strategic sustainable urban planning, and balanced territorial development | It supports the design and implementation of integrated, effective, measurable greening strategies, and the localization of international sustainability targets linked to climate adaptation, biodiversity restoration, integrated finance and urban planning
GC-Plan1-03 | Greening Cities | Action Plan 1 (elaborated in 2024) | Policies for achieving urban restoration targets/Urban Nature Plans | This Action aims to support the implementation of the Urban Nature Plans and urban ecosystem targets as included within the EU Nature Restoration Regulation (NRR) in two distinct ways. Firstly, it will gather examples of and analyse existing policies relevant to the implementation of the targets, and secondly it will input into the Commission’s upcoming work on the definition of a ‘satisfactory level of urban green space and urban tree canopy cover, as described in the NRR. | No | N/A | 1 | 2 | 1 | Strategy/Plan/Roadmap |  | 15/11/2024 | Advanced implementation | 30/6/2026 | Output 1: Policies for achieving urban ecosystem restoration targets •Draft section for handbook Output 2: Defining satisfactory levels of urban green and tree canopy cover Initial Consultations and Proposal Development Final Reporting •Draft section for Handbook | Output 1: Policies for achieving urban ecosystem restoration targets Preparation and Initial Research Stakeholder Engagement and Policy Discussion •Series of webinars/workshops on policies and needs in collaboration with external interviewer •Draft case study template in collaboration with other Action leaders Reporting and Case Study Development •Case study template for cities to be completed and included in final Handbook (Action 6) ¦ •Draft section for handbook •External expert report on policies •Self-Assessmant Tool Output 2: Defining satisfactory levels of urban green and tree canopy cover Initial Consultations and Proposal Development - Series of webinars; Draft proposal(s) ahead of political event Political Engagement and Events | The research conducted on urban greening policies has significantly increased understanding of possible approaches to integrating the Nature Restoration Regulation (NRR) into urban and green policies across EU cities. A series of webinars featuring speakers from all governance levels—from the European Commission to local authorities—provided both GCP members and a wider group of stakeholders with clearer insight into the requirements arising from the NRR, the decisions needed to initiate the preparation of the National Restoration Plans, as well as potential implementation approaches and concrete practices in development of GI. The outcomes of this work will substantially contribute to the development of a comprehensive publication intended to support policymakers in their decision‑making processes. They will also offer valuable input to the European Commission in formulating additional guidelines or specifications related to determining the satisfactory level under the NRR. | No |  | a) Promoting urban policy for the common good, inclusiveness, accessibility, security and equality; c) Supporting effective urban governance, participation, and co-creation; d) Promoting multi-level governance and cooperation across administrative boundaries; e) Harmonising measures at different spatial levels and implementing place-based policies and strategies. | Implementation of this action contributes to the SDG 11, 13 and 15, pathing the way to healthier, more resilient and inclusive cities.
GC-Plan1-05 | Greening Cities | Action Plan 1 (elaborated in 2024) | Enhancing the use of innovative funding to enhance urban authorities to green cities | This Action identifies and shares knowledge on good practices regarding innovative funding to enhance urban authorities’ green infrastructure. It focuses on three main issues. Firstly, it identifies good and bad practices that cities and private investors have experienced in public and private partnerships on green infrastructure projects. Secondly, it examines good and bad practices in the use of debt-based instruments such as green bonds and loans from the Natural Capital Financing Facility (NCFF). Thirdly, it focuses on long-term financial constructions to finance green infrastructure projects and maintenance costs. | No | N/A | 3 | 1 | 2 | Guidance documents/Handbooks |  | 2024-01-11 | Half implementation | 31/10/2026 | M1: Repository of innovative financial mechanisms for GI - 1.1. Fiche package consisting of 10 completed fiches with a detailed explanation about the 10 selected financial mechanisms - 1.2. Instrument matrix providing a user friendly overview with a decision support - 1.3. Memo on how the matrix and fiches can be used M2: Scoping paper for innovative financing tool - 2.1: concise scoping paper | Report 'From Barriers to Drivers - Financing Urban Green Infrastructure through Innovation and Partnership': A practical guide for cities under the Urban Agenda Partnership on Greening Cities. This report provides a concise yet practical guide to help cities mobilise partnerships, diversify financing and build the enabling conditions needed to scale up urban green infrastructure across Europe. | - identification of existing best practices among cities and financial organization; first round table organized with cities and financial organizations to identify the main problem/challenge. - Selection of 10 most innovative financial mechanisms that can be applied for developing and maintenance of urban green infrastructure projects. Decision on the content of the fiches and the matrix. | No |  | b) Enhancing integrated and innovative approaches, notably through financing and in correlation to the green, digital and just transitions. | Financing green infrastructure is crucial to accelerate the development of GI as the foundation for well planned and sustainable future cities.
FOOD-PLAN1-01 | Food | Action Plan 1 (elaborated 2025) | ADVOCACY - Advocating for an EU framework for local food policies | The action aims to develop policy recommendations based on the Partnership’s work across various actions and based on feedback from European cities. The work will include the publication of policy document(s) and a final event in Brussels to engage EU institutions and local leaders. | No | N/A | 1 | 2 | 2 | Policy Recommendations |  | 2025-01-10 | Half implementation | 31/12/2026 | The second phase of the Action focuses on the preparation of a policy paper that will include recommendations derived from all other Partnership workstreams. It will be based on the key results emerging from the Partnership’s other actions. | Two outputs have been delivered under this action. 1)The first output, even if it was not planned as an official output, is the Partnership’s response to the consultation on the new EU Agenda for Cities, submitted in May 2025. This response represents the Partnership’s first advocacy effort, calling for food systems to be recognised as a priority theme in the EU Policy Agenda for Cities. 2) The second output is the policy statement "From EU Policy to Local Action - Building commitment for sustainable Urban Food Systems", published on February 12, 2026. The statement was drafted in October and input was collected from members of the Partnership and Eurocities’ and Iclei's networks. The statement calls for a stronger and more structured involvement of cities in EU food policymaking, highlighting priorities for action across eight key recommendations. Link: https://www.urbanagenda.urban-initiative.eu/news/feeding-future-how-cities-can-shape-europes-food-systems | The statement is being actively disseminated through different networks, with the primary aim of encouraging local authorities to participate as active contributors in the upcoming EU Food Dialogues, providing key inputs to the ongoing European discussions on sustainability, affordability, and nutrition. | No |  | a) Promoting urban policy for the common good, inclusiveness, accessibility, security and equality; d) Promoting multi-level governance and cooperation across administrative boundaries | Some key recommendations of the Policy Statement delivered under Action No. 1, such as recommendation No.4, "Guarantee Universal Access to Healthy and Sustainable School Meals", and Recommendation No. 7, "Unlock the Benefits of Public Land", directly advocate for food systems that are socially inclusive and ensure access to healthy food for all, including marginalized groups. These recommendations contribute to the New Urban Agenda and Habitat III commitment on 'Sustainable urban development for social inclusion and ending poverty".
FOOD-PLAN1-04 | Food | Action Plan 1 (elaborated 2025) | FOOD POLICY - Urban Food Policy Training | Starting from existing resources developed by the Food Trails Horizon 2020 project, the action will create an online and in-person training on how to set up and implement Local Food Policies for partner cities. The learning programme will also lead to the formulation of recommendations for local authorities to be shared at the EU level. | No | N/A | 3 | 2 | 1 | Other | Training modules and materials. | 2025-01-10 | Half implementation | 31/12/2026 | The Partnership is planning the other training modules, both online and in person, according to the timeline included in the Action Plan. | Under this action, two training sessions have already been delivered. 1)The first training session was delivered in person on 13 October 2025 in Milan, during the Milan Urban Food Policy Pact - Global Forum. The training brought together members of the Partnership alongside representatives from various external cities and was structured around two modules: .- Developing Urban Food Policies - Designing Food Waste Actions Link:https://www.urbanagenda.urban-initiative.eu/news/urban-food-policy-training-kicks-empower-sustainable-food-systems 2) The second training session was delivered in person on November 19, 2025, at the University of Barcelona. The training focused on indicators for monitoring urban food policy and was structured into two modules: - Monitoring Urban Food Policy Action - Urban Food Systems and Sustainability Framework Link:https://www.urbanagenda.urban-initiative.eu/news/food-partnership-action-capacity-building-and-knowledge-sharing-barcelona | The first two training sessions have helped city officers, members of the Partnership, and external stakeholders to increase their knowledge and capacity in specific areas of food policy implementation, including the development and design of urban food policies, food waste actions, and monitoring frameworks. | No |  | a) Promoting urban policy for the common good, inclusiveness, accessibility, security and equality; g) Contributing to the acceleration of the implementation of the 2030 Agenda SDGs, the New Urban Agenda and Habitat III principles. | Action No. 4 contributes to the NUA’s pillars of effective implementation through capacity building, knowledge sharing, and stakeholder engagement.
FOOD-PLAN1-06 | Food | Action Plan 1 (elaborated 2025) | INDICATORS - Selecting indicators for urban food systems | The action aims to identify few common indicators to monitor urban food systems that can be widely used to track progress and compare conditions and trends across European cities. The goal is to discuss indicators with cities and EC stakeholders, and to propose one or a set of indicators on urban food systems to be introduced at the EU level- EUROSTAT. | Yes | One of the main decisions taken after the Food TP meeting held in Barcelona in November 2025 was that, rather than simply selecting a few indicators to measure the food dimension of urban food systems, it would first be useful to share and present the current state of play with relevant stakeholders (e.g. JRC, DGs). This should include highlighting: - The diversity of approaches across different EU cities - The specific challenges and needs cities face when measuring the food dimension of urban food systems - What could help improve monitoring and comparability at the EU level This approach would allow for a more comprehensive understanding of existing practices and gaps before moving towards the selection of a common set of indicators. | 3 | 2 | 1 | Policy Recommendations | Training modules and materials. | 2025-01-10 | Initial implementation | 31/12/2026 | The next step under Action 6 is to consolidate and systematise the information gathered to date and prepare a report presenting the current state of play to relevant stakeholders (e.g. JRC, DGs). The report should highlight: - The diversity of approaches adopted by different EU cities - The specific challenges and needs cities encounter when measuring the food dimension of urban food systems - Potential avenues to improve monitoring and comparability at EU level | Key outputs are: 1. Participation in the session “Cleverfood European Roundtable: Measuring Progress on EU and Urban Food Systems”, held at the MUFFP on 15 October 2025. The session provided an opportunity to present the work on indicator development carried out under Action no.6 and discuss approaches to measuring progress on EU and urban food systems. 2.Organisation of a training session on urban food systems indicators, for members of the Partnership and external stakeholders, held on 19 November in Barcelona. The session also provided an opportunity to gather the needs and perspectives of cities on the topic. 3.Organisation of a first meeting with researchers from the FutureFoodS initiative to create synergies and exchanges with their activities on indicators to monitor urban food systems. | Increased knowledge and awareness of existing monitoring frameworks available to cities. | No |  | f) Supporting sound and strategic sustainable urban planning, and balanced territorial development | TBD
6 Active partnerships
13 Actions
reported
March
2026